## Sheet1
Status | Goal | Started | Deadline | Status Reasoning [optional]
1 | Program Backend | 2019-01-23 |  |  | 0 | not started
1 | - Learn Python Flask | 2019-01-30
0 | - Learn how to connect to the server | 2019-01-30 | 2019-02-07
0 | - Reqs for the Backend: | 2019-01-30
0 | -- Connect to device
0 | -- Store data
0 | -- Frontend/Backend Interaction
0 | Program Frontend | 2019-01-23 |  |  | 1 | looked at
0 | - Reqs for the Frontend: | 2019-01-30
0 | -- Learn Angular
0 | -- Create dashboard in Angular
0 | -- Frontend/Backend Interaction
1 | Electronics Design | 2019-01-23 |  |  | 2 | started
3 | - Design Requirements | 2019-01-23 |  | Need to meet with community partner to determine requirements | 3 | stuck
0 | - Brainstorm components and block diagrams | 2019-01-23 |  |  | 4 | almost done
0 | - Weigh the different concepts |  |  |  | 5 | complete
0 | - Develop chosen concept in KiCAD - schematic |  |  |  | 6 | skipped
0 | - Build prototype
0 | - Design production-ready design
0 | Produce
0 | - Find manufacturers
0 | - Get quotes
0 | - Find parts / quotes / get budget
0 | - Order parts
0 | - Manufacture
0 | Deploy